# Zim-Connect Full Implementation Phase Program

## Program Purpose

This program defines the end-to-end execution plan to deliver Zim-Connect from prototype screens to a production-ready super app.

## Program Duration and Structure

- Total duration: **12 months** (can be compressed to 9 with larger team)

- Delivery model: phased releases with overlapping workstreams

- Cadence: 2-week sprints, monthly integration milestone, quarterly go/no-go review

## Delivery Principles

- Deliver thin vertical slices early (usable end-to-end flows)

- Keep architecture modular but avoid premature microservice sprawl

- Prioritize trust systems (identity, security, wallet integrity) from day one

- Ship with feature flags and controlled cohort rollouts

## Workstreams

- Platform Foundations (auth, profiles, shared UI, notifications)

- Chat and Social

- Wallet and Financial Rails

- Commerce and Merchant

- Service Verticals (Health, Housing, Transport, Education)

- Security, Risk, and Compliance

- DevOps, SRE, and Observability

- Data and Analytics

## Phase Plan

## Phase 0: Inception and Foundation (Month 1-2)

### Objectives

- establish engineering foundation

- finalize architecture and operating model

- stand up secure environments and CI/CD

### Scope

- monorepo setup, branch rules, quality gates

- design system token implementation (Modern Heritage)

- auth baseline (register/login/OTP/session)

- app shell and global navigation

- telemetry baseline (logs/metrics/traces)

### Deliverables

- running mobile skeleton app + basic backend

- staging environment with automated deployments

- architecture decision records (ADRs)

- security baseline checklist complete

### Exit Criteria

- successful CI on all main branches

- p95 for basic authenticated APIs under target in staging

- no critical security gaps in baseline review

## Phase 1: Social Core + Wallet Core (Month 3-4)

### Objectives

- launch retention engine (chat)

- launch transactional engine (wallet)

### Scope

- chat: conversations, text, voice notes, delivery status

- translation service integration (Shona/Ndebele <-> English)

- wallet account model and double-entry ledger

- QR payment flow and transaction history

- P2P transfers and red-envelope gifting v1

### Deliverables

- end-to-end social + payment journey

- payment reconciliation jobs

- fraud/risk rule engine v1

### Exit Criteria

- chat delivery success >= 99.5% in pilot

- wallet payment success >= 99.8% in pilot

- audit logs available for all wallet actions

## Phase 2: Commerce and Merchant Operations (Month 5-6)

### Objectives

- activate marketplace transactions

- enable merchant operational workflows

### Scope

- product catalog, search, cart, checkout

- order lifecycle and shipment tracking

- merchant hub: inventory, customer chats, order statuses

- C2C listing and escrow-like payment hold/release v1

### Deliverables

- Zim-Mall MVP (B2C + merchant ops)

- merchant onboarding and verification flow

- commerce analytics dashboard v1

### Exit Criteria

- checkout to delivery flow stable for pilot city

- merchant SLA adherence observable in dashboard

- dispute handling flow operational

## Phase 3: First Deep Services Vertical (Month 7-8)

### Objectives

- prove mini-program depth with one high-value vertical

### Scope (recommended first vertical: Zim-Health)

- provider search and profile verification

- appointment booking (in-person + telehealth)

- family health vault (records, prescriptions, vaccinations)

- insurance copay logic integration (major schemes)

### Deliverables

- Zim-Health MVP available to pilot users

- secure record storage and access controls

- provider operations panel (availability/basic responses)

### Exit Criteria

- successful booking and consultation workflow

- role-based access checks pass security validation

- medical data encryption and auditability verified

## Phase 4: Additional Verticals + Ecosystem Expansion (Month 9-10)

### Objectives

- expand daily utility and network effects

### Scope

- Zim-Housing listings + student housing matching

- Zim-Transport route/ticketing workflows

- Zim-Education fee payment + learning access

- official accounts expansion (agencies, utilities, institutions)

### Deliverables

- at least 3 active service mini-programs

- cross-module unified search and deep-linking

- growth and engagement experimentation framework

### Exit Criteria

- monthly active usage across >= 3 modules per user cohort

- stable cross-module identity/wallet interoperability

## Phase 5: Scale, Hardening, and National Rollout (Month 11-12)

### Objectives

- reach launch-grade reliability and compliance posture

### Scope

- performance optimization and cost tuning

- DR testing and incident response readiness

- compliance/legal sign-off for payments + health data

- city-by-city launch playbook execution

### Deliverables

- production launch checklist complete

- rollback-tested release orchestration

- support operations runbook and escalation matrix

### Exit Criteria

- SLOs consistently met for 30 days

- critical incident MTTR within target

- executive go-live approval

## Program Governance

## Steering Rhythm

- Weekly: delivery standup (engineering leads + product + design)

- Biweekly: sprint review and risk review

- Monthly: architecture and security board review

- Quarterly: executive portfolio checkpoint

## Decision Ownership

- Product scope: Product Director

- Architecture and standards: Chief Architect / Engineering Director

- Security/compliance sign-off: Security Lead + Legal/Compliance

- Launch readiness: Program Steering Committee

## Team Topology and Capacity

- 1 Program Manager

- 1 Product Director + 4 Product Managers

- 1 Design Lead + 4 Product Designers

- 5 Engineering squads (7-9 engineers each)

- 1 Shared Platform/SRE squad

- 1 Security/Compliance pod

- QA embedded in each squad + central test automation support

## Dependencies and External Partnerships

- Mobile money and bank integrations (EcoCash/banks)

- Utility/government official account onboarding (ZETDC, ZIMRA, others)

- Medical aid and provider network integration (CIMAS, PSMAS, providers)

- Logistics and delivery partners for commerce

## Risk Register (Top Risks and Mitigations)

- **Payment integration delays**

- Mitigation: dual-provider abstraction, early certification environment

- **Compliance blockers for wallet/health**

- Mitigation: legal-by-design checkpoints each phase

- **Fraud and trust issues at launch**

- Mitigation: staged limits, verification tiers, anomaly detection

- **Performance bottlenecks under growth**

- Mitigation: load tests each phase + scale playbooks

- **Scope creep across modules**

- Mitigation: strict phase exit criteria and backlog gating

## Quality and Test Program

- Unit, integration, E2E, contract, and security testing pipelines

- Synthetic monitoring for critical user journeys

- Test data strategy for sensitive domains (health, payments)

- Release gates: no unresolved critical defects, no high-risk security findings

## Rollout Strategy

- Internal alpha (staff and controlled merchants)

- City-based beta rollout

- National rollout by cohorts

- Feature-flag rollback per module

## KPI Framework

### Product KPIs

- DAU/MAU, retention D1/D7/D30

- Cross-module engagement rate

- Official account interaction rate

### Financial KPIs

- wallet transaction volume and success rate

- payment dispute rate

- take-rate/revenue per commerce transaction

### Reliability KPIs

- API p95 latency

- crash-free session rate

- incident count and MTTR

### Trust KPIs

- verification completion rates

- fraud loss rate

- account compromise incidents

## 90-Day Immediate Execution Plan (Kickoff)

### Days 1-30

- finalize architecture and domain boundaries

- bootstrap repos/environments/pipelines

- implement auth + app shell

### Days 31-60

- ship chat and wallet skeleton services

- implement ledger model and QR payment prototype

- start merchant and catalog foundations

### Days 61-90

- complete social + wallet pilot flow end-to-end

- run internal UAT with real operational scenarios

- prepare pilot launch readiness package

## Definition of Done (Program Level)

The program is complete when:

- all core pillars (Home, Chat, Wallet, Mall, Services) are operational

- at least one deep service vertical is production-grade

- trust/security controls are certified for launch

- platform meets reliability and performance targets

- support, incident, and operational playbooks are institutionalized